## User Stories
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-M1 | As a support team developer, I want to build a PDF ingestion pipeline and ChromaDB vector store so that company policies can be chunked, embedded, and indexed for semantic search. | MUST HAVE | None | Tushar Agarwal | 3- Completed
S2 | S2 | US-M2 | As a support agent trainee, I want to interact with a persona-driven AI customer simulator that generates replies dynamically while calculating customer sentiment, intent, and retrieving policy citations. | MUST HAVE | US-M1 | Tushar Agarwal | 3- Completed
S3 | S3 | US-M3 | As an active support agent, I want to use a three-panel React workspace console powered by a LangGraph orchestrator to view live tone-specific coaching suggestions and policy compliance checks during conversations. | MUST HAVE | US-M2 | Priya Sharma | 3- Completed
S4 | S4 | US-M4 | As a support QA manager, I want to view post-interaction summaries, sentiment progression graphs, and operations analytics dashboards to review agent performance and resolve knowledge gaps. | MUST HAVE | US-M3 | Priya Sharma | 3- Completed

## Sprint Backlog
Sprint | US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate (Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Sprint 1 | US-M1 | T-M1 | Develop PDF extractor, text chunker (500 limit / 100 overlap), embedding vectorizer, and index them into ChromaDB collection. | 2026-07-06 | 2026-07-17 | Tushar Agarwal | Coding | 3- Completed | 40 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0 | 0 | 0 | 0
Sprint 2 | US-M2 | T-M2 | Implement Groq LLM simulator node with configurable mood rules, intent detection, and citation retriever. | 2026-07-20 | 2026-07-31 | Tushar Agarwal | Coding | 3- Completed | 45 | 45 | 41 | 37 | 33 | 29 | 25 | 21 | 17 | 13 | 9 | 5 | 0 | 0 | 0
Sprint 3 | US-M3 | T-M3 | Build multi-agent LangGraph execution graph (parallel analyzer nodes) and the React three-panel dashboard UI. | 2026-08-03 | 2026-08-14 | Priya Sharma | Coding | 3- Completed | 50 | 50 | 46 | 42 | 38 | 34 | 30 | 26 | 22 | 18 | 14 | 10 | 5 | 0 | 0
Sprint 4 | US-M4 | T-M4 | Develop session QA summary generator, frustration progression visualizers, and operations analytics manager metrics. | 2026-08-17 | 2026-08-28 | Priya Sharma | Coding | 3- Completed | 35 | 35 | 31 | 27 | 23 | 19 | 15 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0

## Impediments
Sprint | Day/Date | Impediment | Action Taken
Sprint 1 | 2026-07-09 | PyTorch/SentenceTransformers imports cause instant container crash (OOM) on Render's 512MB RAM free-tier host. | Implemented environment-detection logic in pipeline.py to bypass model load and fallback to a fast MongoDB text index search.
Sprint 2 | 2026-07-23 | Customer simulator LLM node gets stuck in loops or repeats the agent's statements during conversation tests. | Revised simulator system prompt instructions to penalize repetitive phrasing and lowered LLM temperature to 0.40.
Sprint 3 | 2026-08-07 | LangGraph parallel analysis nodes throw dictionary update conflicts when updating the central state object concurrently. | Implemented a custom merge_logs state reducer function in state.py to join agent execution logs without collisions.
Sprint 4 | 2026-08-21 | Auto-FAQ generator creates duplicate draft cards on overlapping keyword search gap queries. | Added unique database constraints and checked against existing drafted collection records with high similarity (>0.85).

## Retrospective
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-07-06 | 2026-07-17 | Tushar Agarwal | Setup automated unit tests for PDF extraction. | Testing extraction boundaries manually. | Storing file metadata in MongoDB for cataloging. | Integrated pytest in GitHub workflows for automated extraction checks.
2 | Sprint 2 | 2026-07-20 | 2026-07-31 | Tushar Agarwal | Mocking database collections locally to speed up tests when local MongoDB is offline. | Relying strictly on external database connectivity. | Checking simulator mood progressions in isolation. | Created MockDatabase fallback class in database driver.
3 | Sprint 3 | 2026-08-03 | 2026-08-14 | Priya Sharma | Track API token latency logs. | Writing complex nested custom CSS classes. | Using Tailwind CSS variables. | Throttled SSE react state updates.
4 | Sprint 4 | 2026-08-17 | 2026-08-28 | Tushar Agarwal | Automatic backup check on Chroma database indexes. | Manual build deployments without staging verification. | Standardized docker compose configurations. | Wrote deployment setup guide.