## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Priya Sharma | 2026-07-08 | FastAPI fails to launch due to sqlite3 version incompatibility with ChromaDB | Sprint 1 | Tushar Agarwal | Maintainability | Installed pysqlite3-binary and configured patch in chromadb.py launcher | 2026-07-09 | Closed | Verified startup checks execute successfully
2 | Tushar Agarwal | 2026-07-13 | Large PyTorch imports during vector calculations crashRender container (OOM) | Sprint 1 | Tushar Agarwal | Maintainability | Built RAM environment detection to toggle fallback MongoDB keyword text indexes | 2026-07-14 | Closed | Render deployment operates cleanly under 512MB limit
3 | Priya Sharma | 2026-07-22 | Customer Simulator LLM node responds in generic terms disregarding target difficulty setting | Sprint 2 | Tushar Agarwal | Logical | Refactored prompts to enforce strict customer reaction bounds and difficulty mappings | 2026-07-24 | Closed | Verified customer mood progression adjusts accurately
4 | Tushar Agarwal | 2026-08-05 | LangGraph parallel node execution updates overwrite other concurrent results in graph state | Sprint 3 | Tushar Agarwal | Logical | Implemented a custom merge_logs state reducer function in LangGraph definitions | 2026-08-07 | Closed | Parallel node execution works seamlessly
5 | Priya Sharma | 2026-08-11 | SSE token messages cutoff mid-sentence in suggestion box due to buffer limits | Sprint 3 | Priya Sharma | User Interface | Configured React stream reader hook to append and buffer string tokens cleanly | 2026-08-12 | Closed | Verified streaming suggestions display correctly
6 | Priya Sharma | 2026-08-20 | FAQ generation engine creates duplicates on overlapping keyword-gap inputs | Sprint 4 | Tushar Agarwal | Logical | Added unique constraint check querying MongoDB collection prior to draft creation | 2026-08-22 | Closed | Verified duplicate drafts are merged or rejected automatically